## Slide 1: West Michigan Shoreline Materials Management Planning Committee TimeLine Overview December 1, 2025

## Slide 2: Timeline Overview
Legislature Approved Updates to Part 115 MMP: 12/22
Part 115 Takes Effect: 3/23
EGLE Kicks off MMP Process: 1/24
County NOI’s Due to EGLE: 7/24
MMPC Formed & Work Plan Due: 12/24
EGLE releases Work Plan Guidance: 1/25
MMP Work Plan Submitted: 2/25 & EGLE approved: 4/25
Counties receive EGLE Grant Agreements: 5/25
Counties receive executed grant agreements from EGLE: 8/25
Local Government Survey Released & Plan Development Begins: 7/25

## Slide 3: Entities involved in MMP Activities
County Approval Agency
Serves as the primary responsible party.
Responsible for MMP implementation.
Consults with adjacent counties regarding interest in preparing a multicounty MMP.
Appoints the DPA.
Appoints an MMPC.
Oversees the creation and implementation of the DPA’s work program.
Utilizes the MMP Grant funds for MMP development and implementation.
Approves the MMP prior to municipal approval.
Approves MMP modifications, if needed.
Certifies to the Department the progress toward meeting all components of its materials management goals
Designated Planning Agency
Serves as the primary government resource in the planning area for information about the MMP and the MMP development process.
Prepares the MMP work program.
Prepares the MMP.
Consults with all affiliated entities.
Publishes required public notices.
Obtains written approvals from the Planning Committee, CAA, and municipalities.
Manages the public comment process.
Drafts language for review and approval of the Planning Committee.
Ensures approval process and submittals comply with Part 115.
MMP Committee
Directs the DPA in the preparation of the MMP.
Reviews and approves the DPA work program.
Identifies relevant local policies and priorities.
Ensures coordination in the preparation of the MMP.
Advises county (or counties if multi-county) and municipalities.
Ensures that the DPA is fulfilling all the requirements and rules promulgated under this part, as to both the content of the MMP and the public participation requirement.
Notifies the applicable parties of any identified deficiencies.
Approves the MMP prior to public comment.
Provides the final level of approval of the MMP before it is presented for CAA approval.

## Slide 4: Year 1 Timeline We are just Completing Year 1 of 3
Project Timeline/Project Schedule |  |  |  |  |  |  |  | 
 | 2024 |  |  |  | 2025 |  |  | 
Task | Q1 Jan-Mar | Q2 Apr-June | Q3 July-Sep | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-June | Q3 July-Sep | Q4 Oct-Dec
Task 1: Planning Process Initiation | X | X | X | X | X |  |  | 
Task 2: Project Administration | X | X | X | X | X | X | X | X
Task 3: Materials Management Planning Committee |  |  | X | X | X | X | X | X
Task 4: Public Participation/Stakeholder Engagement |  | X | X | X | X | X | X | X
Task 5: Plan Development |  |  |  |  |  | X | X | X

## Slide 5: 3 Year Timeline
Project Timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  | 
Task | Q1 Jan-Mar | Q2 Apr-June | Q3 July-Sep | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-June | Q3 July-Sep | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-June | Q3 July-Sep | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-June | Q3 July-Sep | Q4 Oct-Dec | Q1 Jan-Mar | Q2 Apr-June | Q3 July-Sep | Q4 Oct-Dec
Task 1: Planning Process Initiation | X | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 2: Project Administration | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 3: Materials Management Planning Committee |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 4: Public Participation/Stakeholder Engagement |  | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Task 5: Plan Development |  |  |  |  |  | X | X | X | X | X | X |  |  |  |  |  |  |  |  | 
Task 6: Plan Adoption |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  |  |  |  | 
Task 7: Plan Implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X

## Slide 6: EGLE Plan Format Section Outline
MMP Cover Page
Planning Area Profile
June – December 2025
Materials Management Goals
October 2025 – March 2026
Mechanisms
January – June 2026
Administration
April – October 2026
Appendices
Ongoing

## Slide 7: State-wide Support, Resources, and Coordination
Michigan Association of Regions
Michigan Recycling Coalition
Surrounding Counties
EGLE

## Slide 8: THANK YOU
Stephen Carlson
231-722-7878 ext. 110
scarlson@wmsrdc.org
Erin Kuhn
231-722-7878 ext. 180
ekuhn@wmsrdc.org

## Slide 9: Benchmarking

## Slide 10: Curbside Recycling
Curbside Recycling Access should be calculated for each municipality within the planning area that is either in an urban area or has a resident population greater than 5,000.
If any of these municipalities do not meet the Benchmark Recycling Standards (BRS) of 90% curbside access, the MMP should identify action steps to make progress towards achieving the BRS.

## Slide 11: “Urban” Communities (2020 Census)
“Urban”
Fremont
Ludington
Muskegon-Norton Shores
Whitehall
January 1, 2026: 90% of single-family dwellings must have access to curbside recycling.

## Slide 12: Communities Over 5,000
>5,000
Dalton Township
Egelston Township
Fruitland Township
Fruitport Charter Twp
Laketon Township
Muskegon Charter Twp
Muskegon Heights
January 1, 2028: 90% of single-family dwellings must have access to curbside recycling.

## Slide 13: Drop Off
Counties required to provide a number of drop off locations according to the population of residents without access to curbside recycling.
Locations are available at least 24 hours a month

## Slide 15
County over 100,000 | pop | households | Urban or >5,000 | pop | households | with access | 90% of without | County w/o access
Muskegon County | 176,564 | 75,943 | Dalton Township | 9,481 | 3,628 |  |  | 
 |  |  | Egelston Township | 11,182 | 4,078 |  |  | 
 |  |  | Fruitland Township | 5,831 | 2,585 |  |  | 
 |  |  | Fruitport Charter Township | 14,789 | 5,645 |  |  | 
 |  |  | Laketon Township | 7,647 | 2,960 |  |  | 
 |  |  | Muskegon | 37,203 | 13,721 |  |  | 
 |  |  | Muskegon Charter Township | 17,667 | 7,089 |  |  | 
 |  |  | Muskegon Heights | 9,902 | 3,794 |  |  | 
 |  |  | Norton Shores | 25,000 | 9,761 |  |  | 
 |  |  | Whitehall | 2,974 | 1,156 |  |  | 
 |  |  |  | 141,676 | 54,417 |  |  | 
County under 100,000 | pop | households | Urban or >5,000 | pop | households | with access | 90% of without | County w/o access
Lake County | 12,393 | 4,931 |  |  |  |  |  | 
Mason County | 29,177 | 17,499 | Ludington | 7,664 | 3,565 |  |  | 
Newaygo County | 50,414 | 24,781 | Fremont | 4,532 | 2,044 |  |  | 
Oceana County | 26,788 | 15,645 |  |  |  |  |  |